## Test Scenario
Project Name |  | https://www.demoblaze.com/index.html
Reference Document |  | N/A
Created by |  | Sultan Ahmed
Creation Date |  | 17/09/2022
Date of review
| Test Scenario ID | Test Scenario Description | Priority | Number of Test Cases
| TS_01 | Check that the user can successfully Sign up | P1 | 3
| TS_02 | Check that the user can successfully Log in | P1 | 4
| TS_03 | Check that the user can successfully Log out | P1 | 1
| TS_04 | Check that the user can see the About us video | P1 | 1
| TS_05 | Check that the Contact feature is working correctly | P1 | 3
| TS_06 | Check that Categories panel in the Home page is working correctly | P1 | 1
| TS_07 | Check that user can access all the products information in the Home Page | P1 | 1
| TS_08 | Check that user can successfully add products to the cart | P1 | 1
| TS_09 | Check that the cart feature is working correctly | P1 | 5

## Test Case
Project Name |  | https://www.demoblaze.com/index.html
Reference Document |  | N/A
Created by |  | Sultan Ahmed
Creation Date |  | 18/09/2022
Date of review
Common Steps: 1. Open any browser. 2. Go to this URL https://www.demoblaze.com/index.html
Test Case ID | Test scenrio ID | Test Title | Test Steps | Test Data | Expected Result | Actual Result | Status
TC_01 | TS_01 | Check that the user can Sign up with valid username and password | 3. Click on "Sign up" feature 4. Input Username and Password 5. Click on "Sign up" button | Username: sultan Password: 12345 | After clicking on the Sign up button user should be signed up successfully. | As expected | Passed
TC_02 | TS_01 | Check that the user can Sign up with existing username and password | 3. Click on "Sign up" feature 4. Input existing Username and Password 5. Click on "Sign up" button | Username: sultan Password: 12345 | After clicking on Sign up button, an error message should be shown to the user. | As expected | Passed
TC_03 | TS_01 | Check that the user can Sign up with a null field | 3. Click on "Sign up" feature 4. Input null value 5. Click on "Sign up" button | Username: Null Password: 54321 | After clicking on Sign up button, an error message should be shown to the user. | As expected | Passed
TC_04 | TS_02 | Check that the user can Login with registerd username and password | 3. Click on "Log in" feature 4. Input registered Username and password 5. Click on "Log in" button | Username: sultan Password: 12345 | After clicking on Login button user should be logged in successfully. | As expected | Passed
TC_05 | TS_02 | Check that the user can Login with unregistered username and password | 3. Click on "Log in" feature 4. Input unregistered Username and password 5. Click on "Log in" button | Username: rakib Password: 123 | After clicking on login button, an error message should be shown to the user. | As expected | Passed
TC_06 | TS_02 | Check that the user can Login with wrong password | 3. Click on "Log in" feature 4. Input registered Username with wrong password 5. Click on "Log in" button | Username: rakib Password: 124 | After clicking on login button, an error message should be shown to the user. | As expected | Passed
TC_07 | TS_02 | Check that the user can Login with empty username or password | 3. Click on "Log in" feature 4. Input null value 5. Click on "Log in" button | Username: null Password: 124 | After clicking on login button, an error message should be shown to the user. | As expected | Passed
TC_08 | TS_03 | Check that the user can Logout successfully | 3. Click on "Log in" feature to logged in 4. Click on Logout feature. |  | After clicking on logout button, user should be logged out. | As expected | Passed
TC_09 | TS_04 | Check that the user can acess the video given in About us feature. | 3. Click on "About us" feature 4. Click on "Play Video" icon |  | After clicking on video icon button, the video wil be played and user should be able to stop,pause,forward,backward,minimize and maximize the video. | As expected | Passed
TC_10 | TS_05 | Check that user can send message with correct mail address. | 3. Click on "Contact" feature 4. Input correct Email with Name and Message. 5. Click on "Send message" button | Contact Email: sultan@gmail.com Contact Name: Sultan Message: Hello | The message will succesfully sent and an confirmation message should be shown to the user. | As expected | Passed
TC_11 | TS_05 | Check that user can send message with incorrect mail. | 3. Click on "Contact" feature 4. Input incorrect Email with Name and Message. 5. Click on "Send message" button | Contact Email: sultangmail Contact Name: Sultan Message: Hello | An error message should be shown to the user. | Not as expected | Failed
TC_12 | TS_05 | Check that user can send message with null value in Email, name or message. | 3. Click on "Contact" feature 4. Input null value. 5. Click on "Send message" button | Contact Email: null Contact Name: null Message: null | An error message should be shown to the user. | Not as expected | Failed
TC_13 | TS_06 | Check that the correct products are shown to the user in each catagory. | 3. Click on any button under Catagories panel |  | The products should be shown to the screen as per the selected catagory. | As expected | Passed
TC_14 | TS_07 | Check that user can see the information and price of that product. | 3. Click on any product from product view. |  | The information and price of selected product should shown to the user. | As expected | Passed
TC_15 | TS_08 | Check that user can successfully add products to the cart. | 3. Click on any product from product view. 4. Click ''Add to cart'' button |  | Product should be added to the cart with a confirmation message to the user. | As expected | Passed
TC_16 | TS_09 | Check that user can successfully delete products from the cart. | 3. Click on any product from product view. 4. Click ''Add to cart'' button 5. Click on "Cart" Feature. 6. Click ''Delete'' button |  | Product should be removed from the cart. | As expected | Passed
TC_17 | TS_09 | Check that user can successfully place an order by providing correct information. | 3. Click on any product from product view. 4. Click ''Add to cart'' button 5. Click on "Cart" Feature. 6. Click ''Place order'' button 7. Input valid information 8.Click on "Purchase button" | Name: Sultan Country: Bangladesh City: Dhaka Credit card:7803456782 Month: September Year:2022 | Order should be placed with a confirmation message. | As expected | Passed
TC_18 | TS_09 | Check that user can successfully place an order by not providing any information. | 3. Click on any product from product view. 4. Click ''Add to cart'' button 5. Click on "Cart" Feature. 6. Click ''Place order'' button 7. Input null values. 8.Click on "Purchase button" | Name: null Country: null City: null Credit card:null Month: null Year:null | An error message with some specific requirements should shown. | As expected | Passed
TC_19 | TS_09 | Check that user can successfully place an order by providing wrong information. | 3. Click on any product from product view. 4. Click ''Add to cart'' button 5. Click on "Cart" Feature. 6. Click ''Place order'' button 7. Input incorrect values. 8.Click on "Purchase button" | Name: xyz Country: abc City: pqr Credit card:0000 Month: asf Year:356 | An error message should shown. | Not as expected | Failed
TC_20 | TS_09 | Check that user can successfully place an order with empty cart. | 3. Click on "Cart" Feature. 4. Click ''Place order'' button |  | An error message should be shown because of empty cart. | Not as expected | Failed

## Bug report
Project Name |  | https://www.demoblaze.com/index.html
Reference Document |  | N/A
Created by |  | Sultan Ahmed
Creation Date |  | 30/09/2022
Date of review
Common Steps: 1. Open any browser. 2. Go to this URL https://www.demoblaze.com/index.html
Bug Id | Test Case Id | Bug Title | Bug Description | Reproducing Steps | Enviroment Details | Expected Result | Actual Result | Severity and Priority | Assignee
B_01 | TC_11 | User can send message with incorrect mail. | Users can send message to the website with incorrect mail address. Users should not be able to send message if mail address is not correct. | 3. Click on "Contact" button 4. Input incorrect mail address and other information. 5. Click on "Send message" button | Os: Windows Browser: Chrome | An error message should be shown to the user. | Not as expected | S1,P4 | Developer
B_02 | TC_12 | User can send message without inputting any information. | Users can send message to the website with null values in Contact mail, name message. Users should not be able to send message if they don't provide any information. | 3. Click on "Contact" button 4. Click on "Send message" button | Os: Windows Browser: Chrome | An error message should be shown to the user with some specified requirements. | Not as expected | S1,P4 | Developer
B_03 | TC_19 | User can place an order with wrong information. | Users can place order with invalid information. Users should not be able to place an order if they don't provide correct information. | 3. Click on any product from view 4. Click on "Add to cart" button 5. Click on "Cart" button 6. Click on "Place Order" button 7. Input wrong information 8. Click on "Purchase" button | Os: Windows Browser: Chrome | Order should not be placed. An error message should be shown to the user. | Not as expected | S1,P1 | Developer
B_04 | TC_20 | User can place an order with empty cart. | Users can place order with empty cart. Users should not be able to place an order if they don't have added any product to the cart. | 3. Click on "Cart" button 4. Click on "Place Order" button | Os: Windows Browser: Chrome | An error message should be shown to the user for empty cart. | Not as expected | S1,P1 | Developer